## Defect Log
Defect ID | Linked Test Case ID | Defect Summary | Detailed Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Reported By | Assigned To | Sprint | Environment | Date Reported | Date Closed | Comments
DEF-001 | TC-CHK-004 | Delivery address not persisting after refresh | Selected whitelist address disappears after page refresh | 1. Place order 2. Change address using Set B 3. Refresh Orders page | Updated address should persist | Address resets to previous value | High | P1 | Open | QA | Backend Dev | Sprint 2 | Local (XAMPP) | 2026-01-18
DEF-002 | TC-CART-002 | Cart total not displayed | Total price missing in cart API response | 1. Add product to cart 2. Call cart_api GET | Total should be calculated and returned | Only item list returned | Medium | P2 | Fixed | QA | Backend Dev | Sprint 1 | Local (XAMPP) | 2026-01-15 | 2026-01-16 | Verified in re-test